## Slide 1: Project Update2: Team #2 / UCONNIC Induction Submission Project
Sponsor: Allen Nobody
Project Manager: Akshay Raj
Data as of: 28 August 2022
Data pre-processing is done using data transformation/visualization techniques as part of data cleaning along with the prioritization of required fields.
Consulted the UCONNIC team to proceed further in the creation of a finished model.
Created a model for converting the hand-written text into the typed format using Optical Character Recognition (OCR) and Natural Language Processing (NLP) techniques.
Integration of OCR and NLP is accomplished into the data model to decide the optimal modeling technique.
The training model is subjected to its first iteration.
Project Status
Gantt Chart developed.
Project Baseline established.
Data Processed, Transformed and Visualized.
Optical Character Recognition System Developed
Natural Language Processing System Developed
Optimum modeling technique finalized.
Key Achievements this period
Key Performance Indicators |  |  | 
Indicator | R | C | O
Overall | G | G | 
Scope | G | G | 
Budget | G | G | 
Schedule | A | G | 
Risks | G | G | 
Dependencies | G | G | 
Other | N/A | N/A | N/A
Other | N/A | N/A | N/A
Top Risks and Issues |  |  |  | 
R/I | Risk | P | I | Response Action
I | Time management in accomplishing tasks due to delay triggered by late NDA submission. |  | L | Work on task pipe-lining to make sure the project date is not extended.
R | Data provided may not be enough to train model. | L | H | Necessary RMSE errors are taken into consideration as cut-offs. If not sufficient, then champion will be requested for additional data
R | The finalized model may not reach the stakeholder’s expectations. | L | M | Schedule regular short calls with the stakeholders & UCONNIC SMEs so that the feedback is taken periodically.
Assess the model with UCONN SMEs and proceed further in training the model.
Validate and test the model after training it on multiple iterations.
Review the validated and tested models with stakeholders.
Planned for next period
We have come up with a complex model with high accuracy but is hard to modify in the future, and the other one is a simple model with moderate accuracy but is easy to modify in the future. How would you trade-off between these two situations and decide which one is expected?
Questions for Sponsor