## Slide 1: Project Update: Team #2 / UCONNIC Induction Submission Project
Sponsor: Allen Nobody
Project Manager: Akshay Raj Pallerla
Data as of: 6 November 2022
The OCR tool for data scrubbing is working as expected with accuracy of 98%
The overall desired accuracy of the model has not been achieved yet
Five out of the twenty fields have demonstrated an accuracy of over 90%
Eight out of twenty fields have demonstrated an accuracy between 75% and 90%
Six out of twenty fields have demonstrated an accuracy of over 50% and 75%
UCONNIC SMEs have been consulted to assess the model
The model is subjected to its final iteration of training
The training model is subjected to its first iteration
Project Status
Three out of four iterations of training for the model were completed
Accuracy of more than 90% for 5 fields achieved
Key Achievements this period
Key Performance Indicators |  |  | 
Indicator | R | C | O
Overall | G | G | 
Scope | G | A | 
Budget | G | G | 
Schedule | G | G | (
Risks | G | G | 
Dependencies | G | G | 
Other | N/A | N/A | N/A
Other | N/A | N/A | N/A
Top Risks and Issues |  |  |  | 
R/I | Risk | P | I | Response Action
I | Model not accurately trained |  | H | Final iteration of training to be completed
I | The Exposure field has a low accuracy (31%) after the third iteration of training |  | L | Do not consider the Exposure field for machine learning entry
R | Employee/End User Training Failure | L | M | Identify the problem with employees and change in training material if required
R | UCONNIC system integration failure | L | H | Communicate the system requirements and make experts available
Complete the final iteration of training for the model
Assess the final model with UCONNIC SMEs
Validate and test the final model
Train Genpact Users
Integrate final model
Planned for next period
We are on track to have 95% accuracy of at least 7 of the 20 fields without any changes in budget or time, otherwise we may need to implement a change control regarding either budget, time, or both. Is having 7 fields acceptable by Allan or should we implement the change?
Questions for Sponsor