## Slide 1
Case for change / Problem Statement
Inducing information from emails and attachments is time-taking, tedious and demands more labor. Manual interpretation costs huge amount of money and has highly potential for data entry errors.
Business Case
The discounted payback period of the project is 1.37 years, with a working cost of capital = 7.5%, a yearly savings of $240,000, and a $300,000 initial expenditure. This initiative will save $240,000 per year by cutting 40% of labor expenditures ($30000 per employee) due to application processing staffing. The AI model's induction of 95 percent error-free data into the underwriting system will result in increased efficiency and time and money savings due to fewer errors.
Objectives / Goal statements
Develop an AI model which can automize at least 10 fields with a reach goal of 20 fields. Develop a machine learning system that can retrieve the data with an efficiency of 95% by 14 Feb 2023 with a budget of $300,000. Train the GENPAT staff with the integrated model and make it ready to use for the incoming data.
Top Risks (max. 5)
Data provided i.e.; 400,000 applications may not be sufficient to train the model Possibility of data leak Change in stakeholder expectations can change the scope of the project. Provided data has errors that decrease the efficiency of the model when trained with it. Reduction of model performance due to incompatibility of it with systems at GENPACT
In Scope | Out of Scope
Machine learning for a specific language(English) | Machine learning system for different languages.
Training machines to reduce errors, save time, and improve timeliness | Delivery of model to integrate to different external interfaces
Process at least 10 fields | Process additional fields other than the 20 mentioned by Allen
Constraint Matrix |  |  | 
 | MOST | SOME | LEAST
SCOPE |  |  | X
TIME | X |  | 
COST |  | X | 
UCONNIC Submission Induction Project Charter:

## Slide 2
Deliverables & Milestones (High Level Milestone Plan) |  |  | 
Project Start Date: 20 Feb 2022 |  | Project End Date: 14 Feb 2023 | 
Key Deliverable | Milestone Name (MN) |  | Planned MS Date
Approval of Project Charter | Project Charter approved |  | 31 Mar 2022
Cleaned Data | Data is cleaned |  | 15 June 2022
Training the model with the data | Model is Trained |  | 20 Sep 2022
Updating members of the organization about the progress of model | Update on model received by Organization |  | 15 Oct 2022
Final Model | Model finished |  | 10 Dec 2022
Training staff members on new model | Staff Trained on new model |  | 05 Jan 2023
Implementing model in daily workflow | Model implemented |  | 14 Feb 2023
Incoming Dependency | Outgoing Dependency
Allen to provide the data required to train the system | Delivering the model to integrate to AWS(Amazon Web Services)
Necessary approvals and communications to share information required for the project | -
The expertise of SMEs from UCONNIC | -
Signoff |  | 
Role | Signature | Date
Sponsor |  | 
PSB Member |  | 
Beneficiary |  | 
Beneficiary |  | 
Project Organization | 
Sponsor | Allen Nobody, COO
PSB Members | CIO, CUO, COO
Project Manager | Akshay Raj Pallerla
Workstream Leaders | None
Team Members | Akshay Raj Pallerla
Assumptions
Errors in the provided data will not impact the model performance 400,000 applications are enough to train the model Have enough technical resources for Genpact to maintain the new model in a production environment Project champion is available to timely respond to all the questions and provide required guidance , resources to the project team.
UCONNIC Submission Induction Project Charter: