## FMEA Template
FAILURE MODES & EFFECTS ANALYSIS WORKSHEET
Process / Product: | UCONNIC Submission Induction Project / Group 2 |  |  | FMEA Date (Original): 22 September 2022
WHEN Item/ Process Step | WHAT Potential Failure Mode | Potential Effect(s) of Failure | Severity | WHY Potential Cause(s) of Failure | Occurrence | Current Controls | Detection | RPN | Recommended Actions (Response Plans - Containment, SOP's, Control Plans) | Responsibility and Target Date Completion | Action Taken | Severity | Occurrence | Detection | RPN
3-Model Training | Model not accurately trained | Severe delays in project timeline | 7 | Not enough data received | 2 | Allen will offer more data as it is created if requested | 5 | 70 | Accept Risk | Colby-5/2/2022 | We have come up with an after-action review and had some avoidance measures to maintain transparency within the team. | 7 | 2 | 5 | 70
3-Model Training | Model not accurately trained | Severe delays in project timeline | 7 | Quality of data poor | 3 | Data cleaning and sorting | 5 | 105 | Increase screening of data before cleaning | Colby- 5/2/2022 | Data was screened prior to scrubbing. Outliers were removed. | 7 | 2 | 3 | 42
2-Data Scrubbing | Violated NDA | Legal action and project restart. Loss of intellectual property | 7 | Leaked data by employees | 1 | Variable authority on data based on employee role | 6 | 42 | Design a proprietary algorithm that discloses limited information only to specific people/leadership who are accountable for the data | Colby- 04/01/2022 | Responsible person to communicate with the employees on the consequences of violating an NDA | 7 | 1 | 4 | 28
1-Data Receipt | Data delivery late | Delays in project timeline | 5 | Delay in legal process | 5 | None | 1 | 25 | Assign a team member responsible for follow-up and get the NDAs signed on time | Colby- 04/01/2022 | A new role in the team has been created whose responsibility is to communicate any new project-related updates or announcements and maintain transparency in the team. | 5 | 3 | 1 | 15
1-Data Receipt | Data delivery late | Delays in project timeline | 5 | Hardware constraints | 5 | None | 3 | 75 | Increase the system parameters like maintaining high-end graphic-card, high RAM and enough cloud storage. | Akshay- 04/01/2022 | Upgraded graphic card and increased the size of the cloud storage to backup the data | 5 | 4 | 3 | 36
5-Project Delivery | Communication Gap | Delays of deliverables | 4 | Difference in timezones | 5 | Follow a common timezone irrespective of the country in communication platforms. | 1 | 20 | Reduce the communication channels to least number possible and have regular feed-back calls | Akshay- 01/12/2023 | The schedule for connecting on the Microsoft Teams platform has been fixed. | 4 | 3 | 1 | 12
3-Model Training | Employee Resource crunch | Delays in project timeline | 5 | Employee turnover | 6 | Monitor toxic employees, reward employee credibility | 1 | 30 | Sign up with employees to have a 2year work contract while hiring and in worst-case scenarios try to enable some promising free-lancers who might look for a long term opportunity in the organization. | Kranthi-04/15/2022 | Prepared a non-disclosure agreement (NDA) for all employees, which must be signed by the employee at the time of hire. | 5 | 4 | 1 | 20
3-Model Training | Poor Quality of Data | Creation of an overfitted/undersampled model | 5 | Frequent missing information/not enough content in the data | 3 | Perform Data Quality Assurance process as part of the initial investigation whenever data is received | 7 | 105 | Try in-depth data exploration techniques and contact the champion for more data | Kranthi-04/15/2022 | Performed in-depth action approaches and gathered data from the champion, resulting in higher data quality. | 5 | 2 | 5 | 50
3-Model Training | Project cost escalation | Budget constraints not met | 6 | Too much Project Crashing | 5 | A periodic check on cost performance indexes using Earned value method | 2 | 60 | Implement some cost-cutting techniques and job-rotation strategies | Kajol-5/2/2022 | The cost was calculated using the earned value analysis approach, which ensured that the cost was balanced. | 6 | 4 | 2 | 48
2-Data Scrubbing | Pre-processing complications | Inaccurate Model | 6 | Unformatted Data | 3 | Use some benchmarking techniques with reference to some open-source models and validate model performance | 5 | 90 | The team must work with relative data scientists so that what level of data cleaning is suitable for them to work upon | Deepa- 06/08/2022 | Analyzed the root cause and found that the complications were due to missing data and regional formats. The team has worked on it and had minimized the complications. | 6 | 2 | 4 | 48
3-Model Training | Software crash/other software related problems | Delay of deliverables | 7 | Unexpected behavior in machine learning algorithms. | 3 | Construct optimized algorithms which could consume less software threads | 7 | 147 | Upgrade to the latest graphics cards and software to increase system performance. | Akshay-5/2/2022 | Discussed the requirements with the data scientists and upgraded the systems to NVIDIA Tesla K80 graphic card, and increased thread count in the software to 100,000 kernel threads. | 7 | 3 | 4 | 84
2-Data Scrubbing | Overfitting and higher bias | Inaccurate Model | 6 | Biased content in the historic data | 3 | Random Sampling of Data | 8 | 144 | Use the cross-validation technique and train with more data | Kajol- 06/08/2022 | Used regularization and ensembling techniques along with validation techniques | 6 | 3 | 6 | 108
5-Project Delivery | Complication in integration with UCONNIC system | Project delay | 7 | unavailability of hardware and software resources. | 4 | None | 5 | 140 | Having SME ready to mitigate the errors occured | Deepa-01/12/2023 | Communicated with UCONICC about the requirements of the systems and made experts available | 7 | 3 | 4 | 84
2-Data Scrubbing | Security breach & data leakage | Inappropriate usage of exposed information | 7 | Improper authorizations related to the system | 3 | Secure passwords and authentication are implemented | 3 | 63 | the team must work with cybersecurity and mitigate the data loss | Kajol- 06/08/2022 | Cybersecurity software has been deployed | 7 | 2 | 2 | 28
2-Data Scrubbing | Security breach & data leakage | Inappropriate usage of exposed information | 7 | Weak/Stolen credentials | 3 | Controlling access to data | 3 | 63 | Introduce 2-way authentication method | Akshay- 06/08/2022 | 2-way and 3-step authentication were implemented | 7 | 2 | 3 | 42
2-Data Scrubbing | Security breach & data leakage | Inappropriate usage of exposed information | 7 | Back door application vulnerabilities | 3 | Secure the data while transmitting | 3 | 63 | Segmenting network and monitor who’s trying to get in and out | Colby- 06/08/2022 | used firewalls and intrusion detection and prevention tools | 7 | 2 | 3 | 42
2-Data Scrubbing | Security breach & data leakage | Inappropriate usage of exposed information | 7 | Insider threats | 3 | Proactively train the staff and conduct an insider threat self-assessment | 3 | 63 | Cybersecurity packages and security audits should be installed | Kranthi- 06/08/2022 | Implemented security software and appliances | 7 | 2 | 3 | 42
3-Model Training | Operational risks | Poor and unorganized implementation of critical operations and other core processes | 7 | Difference in opinion of project team | 6 | Receive feedback from multiple teams | 1 | 42 | Maintain periodic meetings to discuss the ideas from different teams | Akshay-5/2/2022 | Maintained good communication and discussed different opinions to get feedback periodically | 7 | 2 | 1 | 14
3-Model Training | Change in the project constraints | Project constraints not met | 6 | Scope Creep | 6 | None | 3 | 108 | Mitigate - Discussion with Champion | Akshay 5/2/2022 | Pending | 6 | 6 | 3 | 108
3-Model Training | Lack of Model Fine Tuning | Inaccurate Model | 6 | Lack of enough metrics to assess the model quality. | 3 | Troubleshooting the issue for inaccuracy | 2 | 36 | Avoid - quality checking in each step of model development | Kajol 5/2/2022 | Troubleshooting the issue for inaccuracy | 6 | 2 | 2 | 24
2-Data Scrubbing | Privacy Laws Violated | Subjecting to legal penalties | 8 | Varying country-specific privacy laws | 2 | Have the legal team verify the privacy laws periodically | 6 | 96 | Maintain documentation and update it periodically on the privacy laws for every country in which the project is rolled-out | Deepa 4/15/2022 | Pending | 8 | 1 | 6 | 48
4-Genpact Training | Employee/End User Training Failure | Poor utilization of the model | 6 | Employees trained improperly | 5 | Change of training material | 4 | 120 | Get the feedbacks from Genpact employees and improve shadowing process. | Kranthi 12/20/2022 | Understanding the problem with employees, and bringing the relevant SMEs to realize what exact areas to focus-on. | 6 | 4 | 4 | 96
4-Genpact Training | Employee Resource Crunch | Delays in project timeline | 5 | Low Budget | 6 | Help from resources from different team | 2 | 60 | Mitigate - Look for available resource from different team | Colby 12/20/2022 | Help from resources from different team | 5 | 2 | 3 | 30
3-Model Training | Misinterpretation of data | Model does not satisy scope | 6 | Limited knowledge of important fields | 3 | Meeting with SME to understand the data | 4 | 72 | Mitigate - Meeting wih SME | Deepa 5/2/2022 | Meeting with SME to understand the data | 6 | 3 | 2 | 36
5-Project Delivery | Communication errors between GENPACT, Underwritng, and our team | Delays of deliverables | 4 | Misscheduling and/or schedule conflicts | 5 | Create effective pre -project planning | 3 | 60 | Collaborate and communicate with other project managers and team members | Akshay-01/12/2023 | Communication is done with the project managers and team members | 4 | 2 | 2 | 16
3-Model Training | Unavailability of subject matter expert. | Errors and inaccuracies in training model iterations | 7 | SME overloaded | 3 | RCI Matrix | 3 | 63 | Search for the right SME and collaborate with him | Kranthi-5/2/2022 | Selected the proper subject matter expert with the necessary skills to complete the assignment. | 7 | 2 | 2 | 28
2-Data Scrubbing | Inadequate GPU processors for cleaning large data sets. | Delays in project timeline | 5 | Data set too large | 3 | Data compression | 2 | 30 | Create clusters in the cloud which handle the workload | Kajol- 06/08/2022 | Compressed data which reduced the file size and helped in speeding up the process | 5 | 3 | 1 | 15
5-Project Delivery | Poor Communication with the Customer | Effects customer trust | 5 | No Change Control process established | 4 | Collect reviews and improve loyalty | 4 | 80 | Take action on the feedback and provide top-notch customer service | Deepa-01/12/2023 | Collected feedback and took action to satisfy the needs of the customer | 5 | 3 | 3 | 45
3-Model Training | Failure to capture data from all applications | Inaccurate Model | 6 | Model not developed for different submission formats | 3 | Building a model which accepts all formats of data by pre-processing | 2 | 36 | None - Accept risk | Kranthi-5/2/2022 | Discuss with the project champion and all the stakeholders on the decision in accepting the risk | 6 | 3 | 2 | 36

## Operational Definitions
Severity Ratings
Effect | Rank | Criteria
Very High | 9 - 10 | Failure affects safety or involves noncompliance to government regulations. May endanger machine or assembly operator (9 with warning, 10 without warning)
High | 7 - 8 | High degree of customer dissatisfaction due to the nature of the failure, such as inoperable item or system. Failure does not involve safety or government regulation. May result in serious disruption to subsequent processing or assembly operations and/or require major rework.
Moderate | 4 - 5 - 6 | Failure causes some customer dissatisfaction which may include discomfort or annoyance. Customer will notice item or system performance deterioration. This may result in unscheduled rework/repair and/or damage to equipment.
Low | 2 -3 | Due to the nature of this failure, the customer experiences only slight annoyance. Customer will probably notice slight deterioration of the item or system performance or a slight inconvenience with a subsequent process or assembly operation, i.e. minor rework.
Minor | 1 | Unreasonable to expect that the minor nature of this failure will have any noticable effect on item or system performance or subsequent process or assembly operation. Customer will most likely not be able to detect the failure.
Occurrence Ratings
Occurrence Ratings | Rank | Criteria | Failure Rates
Very High | 10 | Failure is almost inevitable | >1 in 3
| 9 |  | 1 in 6
High | 8 | This process or similar processes have often failed | 1 in 15
| 7 |  | 1 in 50
Moderate | 6 | This process or similar processes have experienced occasional failures, but not in major proportions | 1 in 150
| 5 |  | 1 in 800
| 4 |  | 1 in 4,500
Low | 3 | Isolated failures associated with similar processes | 1 in 30,000
Very Low | 2 | Only isolated failures associated with this process or almost identical processes | 1 in 150,000
Remote | 1 | Failure unlikely. No failures ever assocaited with this process or almost identical processes | <1 in 1,500,000
Detection Ratings
Detection | Rank | Criteria
Absolute certainty of non-detection | 10 | Controls will not or can not detect the existence of a failure. No known controls available to detect failure mode.
Very low | 9 | Controls probably will not detect the existence of failure mode
Low | 7-8 | Controls have a poor chance of detecting the existence of failure mode
Moderate | 5-6 | Controls may detect the existence of a failure mode.
High | 3 - 4 | Controls have a good chance of detecting failure mode, process automatically detects failure mode.
Very High | 22 | Current controls almost certain to detect the failure mode. Reliable detection controls are known with similar processes. Process automatically prevents further processing.